## Instructions
This EXCEL spreadsheet has been set up so that you can enter your progress for 25-26 and 26-27 by Goal, Strategy and Action. Information provided during the first 3 years of this five year plan is already entered, according to the Actions included in this LIS Marine Debris Action Plan - Mid-year Revision.
1. Review the revised LIS Marine Debris Action Plan, dated August 2025 to determine the relevant goal(s), strategy(ies) and action(s) you would like to report on. The plan lists the metrics that are included in the EXCEL spreadsheets.
2. The EXCEL file has separate worksheets for each Strategy under each Goal. Select the correct worksheet and make sure that you are entering your information for the correct Strategy, Action and year.
3. Enter your metrics as available for each Action and list your name/organization under "Contributors" to indicate you have entered information for thie reporting year. If someone has already entered numbers for the metrics, just add your numbers to them.
4. If you want to provide a link or make a comment, do so under the relevant column "Comments/Links" for the relevant year, to the right of "Contributors".
5. Save and then move on to the next Action you wish to report on, following the same directions.
If you are a team of organizations working together (e.g., the LTRAP group), please have one person enter all of the data for the team to avoid duplication.
Thank you!
Link to Long Island Sound Marine Debris Action Plan: | https://marinedebris.noaa.gov/regional-action-plans/long-island-sound-marine-debris-action-plan
Link to Sheet | Definition
Goal 1: Understand, Prevent and Mitigate the Impacts of Single-Use Plastic and Other Water/ Land-based Consumer Debris
Goal 1 Strategy 1 | Strategy 1.1 Prevention, Education and Outreach
Goal 1 Strategy 2 | Strategy 1.2 Research Assessment, Wildlife Impacts and Monitoring
Goal 1 Strategy 3 | Strategy 1.3 Proper Disposal and Infrastructure
Goal 1 Strategy 4 | Strategy 1.4 Removal
Goal 1 Strategy 5 | Strategy 1.5 Policy and Management
Goal 2: Understand, Prevent and Mitigate the Impacts of Abandoned and Lost Fishing/ Aquaculture Gear
Goal 2 Strategy 1 | Strategy 2.1 Prevention, Education and Outreach
Goal 2 Strategy 2 | Strategy 2.2 Research Assessment, Wildlife Impacts and Monitoring
Goal 2 Strategy 3 | Strategy 2.3 Proper Disposal and Infrastructure
Goal 2 Strategy 4 | Strategy 2.4 Removal
Goal 2 Strategy 5 | Strategy 2.5 Policy and Management
Goal 3: Understand, Prevent and Mitigate the Impacts of Microplastics and Microfibers
Goal 3 Strategy 1 | Strategy 3.1 Prevention, Education and Outreach
Goal 3 Strategy 2 | Strategy 3.2 Research Assessment, Wildlife Impacts & Monitoring
Goal 3 Strategy 3 | Strategy 3.3 Source Reduction
Goal 3 Strategy 4 | Strategy 3.4 Policy and Management
Good Ideas but no Partners

## Goal 1 Strategy 1
Goal 1: Understand, Prevent and Mitigate the Impacts of Single-Use Plastic and Other Water/ Land-based Consumer Debris
Strategy 1.1 Prevention, Education and Outreach
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
1.1.1 | Research and review existing communication/outreach materials, educational programs, activities and intervention products that are relevant to and could be replicated across the Long Island Sound region and make links to them available to partners through listserv messages and website postings. | # links to resources shared or posted annually
1.1.2 | Adapt existing or create new communication/outreach products including social media campaigns on consumer debris and single-use plastic and disseminate to urban, inland and coastal communities. | # outreach products adapted/created
# products distributed
# people engaged
# adapted or new social media campaigns implemented
# social media posts shared
1.1.3 | Engage Long Island Sound watershed residents in meaningful interactions through outreach activities to promote source reduction of common consumer debris items, including single-use plastic and encourage increased use of sustainable alternatives such as reusable items. | # people engaged in meaningful interactions
# outreach activities
1.1.4 | Launch a pilot project employing the principles of Community Based Social Marketing that leads to the reduction of consumer debris through behavior change. (Crosscuts with 1.2.2) | # pilot projects launched
# evaluations completed
1.1.5 | Host events that promote source reduction of common consumer debris items, including single-use plastic, and encourage increased use of sustainable alternatives such as reusable items. | # events hosted
# people engaged
1.1.6 | Adapt/create and implement outreach campaigns to share alternatives to the intentional release of balloons using strategies developed with local or regional partners. (Crosscuts with 1.2.2). Note that Connecticut currently prohibits the intentional release of 10 or more balloons while New York has both state and local bans on individual releases. | # campaigns implemented
1.1.7 | Adapt/create and disseminate educational resources about sustainable and waste-reducing initiatives that can be utilized by partner organizations to reduce consumer debris and single-use plastic in everyday operations and hosted events. | # resources created/adapted & disseminated
# partners employing initiatives
1.1.8 | Inventory/analyze existing consumer debris education resources to determine what is available and appropriate for P-12 students. | # existing resources inventoried/analyzed & appropriate for P-12 students
1.1.9 | Review/share existing or develop new resources to inform policy related to consumer debris and disseminate to local municipalities and policymakers. | # policymakers engaged
# resources developed/shared
1.1.10 | Adapt/create and disseminate educational materials focused on source reduction/prevention of consumer debris and single use plastic for P-12 students that align with Next Generation Science Standards where applicable, and that have been successfully demonstrated through online platforms, in-person events, educator workshops, after-school programs and visits, summer camps, campaigns and field trips to P-12 educators and Long Island Sound watershed students. (Crosscuts with 3.1.2) | # education materials created / adapted
# P-12 educators engaged
# P-12 students engaged
1.1.11 | Share and promote, through established or new listservs and websites, professional development opportunities for or by educators focused on single-use plastic and consumer marine debris reduction and education with high schools and universities across the Long Island Sound watershed region. | # high schools reached
# universities reached
# professional development opportunities shared
1.1.12 | Create/adapt and disseminate outreach materials to support campaigns promoting reduction of single-use plastic use by the food service, travel and tourism industries. (Crosscuts with 1.2.2) | # outreach materials created/adapted & disseminated
# campaigns supported
1.1.13 | Engage private sector partners in the food service, travel and tourism industries in conversations to implement single-use plastic reduction practices, understand barriers to implementation and share lessons learned with Long Island Sound watershed partners and the public. | # private sector partners engaged
1.1.14 | Identify tools that prevent or reduce single-use plastic from entering the watershed, research existing/create new inventory of intervention products and highlight these resources on websites and in brochures. | # tools identified
# inventories created/shared and updated annually
# brochures distributed
# website visits
1.1.15 | Review marine debris data reported to the Ocean Conservancy International Coastal Cleanup database and the University of Georgia Marine Debris Tracker annually to inform the Long Island Sound Partnership’s Marine Debris Ecosystem Target and highlight results. | # annual report submitted for LISP ecosystem target for marine debris
# new indicators developed using data
1.1.16 | Highlight and share links to NOAA Marine Debris Program resources on marine debris emergency preparedness for storm events and other natural disasters. | # links shared
# links updated

## Goal 1 Strategy 2
Goal 1: Understand, Prevent and Mitigate the Impacts of Single-Use Plastic and Other Water/ Land-based Consumer Debris
Strategy 1.2 Research Assessment, Wildlife Impacts and Monitoring
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
1.2.1 | Compile existing consumer debris information and wildlife impacts annually and make them available to facilitate analysis of information gaps, best practices and available resources. | # links to resources posted
1.2.2 | Analyze annually the effectiveness of community-based social marketing techniques and behavior change consumer debris campaigns that encompass Long Island Sound watershed communities and undertaken through Actions 1.1.4, 1.1.6 and 1.1.11. | # campaign effectiveness evaluations completed
1.2.3 | Seek/share grant opportunities to address Action Plan research priorities, including research that: | # funding opportunities shared
| Identifies and addresses knowledge gaps so that new consumer debris efforts can be launched that successfully support Actions 1.1.2 and 1.1.3. | # proposal submitted
| Improves understanding of the impacts of consumer debris on wildlife to inform public outreach campaigns and policymakers | # proposals funded
| Identifies more sustainable alternatives to recycling | # partners engaged
Identifies and/or informs interception technology effectiveness or alternatives that focus on consumer debris to better inform decision-makers and raise public awareness.
1.2.4 | Promote community science programs that collect data on marine debris to better inform decision-makers and raise public awareness. | # community science programs promoted
# people engaged
1.2.5 | Survey local and state policies and management plans aimed at source reduction, prevention and interception practices using available data and information. This will inform Action 1.5.2. | # new policies related to marine debris

## Goal 1 Strategy 3
Goal 1: Understand, Prevent and Mitigate the Impacts of Single-Use Plastic and Other Water/ Land-based Consumer Debris
Strategy 1.3 Proper Disposal and Infrastructure
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
1.3.1 | Support the development and installation of interception technologies, tools, receptacle bins and capture devices that support data collection and monitoring across the Long Island Sound watershed. | # developed
# installed
1.3.2 | Support the installation, maintenance and proper use of cigarette disposal receptacles in communities, parks and beaches (in collaboration with smoke-free beach resolutions as appropriate) to limit butts entering the environment. | # parks, beaches, towns or communities with new receptables
# new receptacles installed
1.3.3 | Facilitate/support other removal actions (e.g., signage, recycling bins) at the local level that divert debris from entering Long Island Sound and its watershed. | # local removal actions diverting debris from LIS
1.3.4 | Identify and engage with boating organizations and marinas to support the installation, maintenance and proper use of disposal bins for boaters. | # boating organizations/marinas engaged
# disposal bins installed
1.3.5 | Engage managers of state and municipal public parks and beaches with concession stands in pilot programs to reduce use of single- use plastic products and promote as ‘eco-friendly’ or ‘don’t trash the beach’ locations. | # pilot programs at beaches/parks
1.3.6 | Identify and share opportunities for vessel shrink wrap recycling with Long Island Sound residents. | # shrink wrap recycling opportunities shared
# pounds of shrink wrap recycled

## Goal 1 Strategy 4
Goal 1: Understand, Prevent and Mitigate the Impacts of Single-Use Plastic and Other Water/ Land-based Consumer Debris
Strategy 1.4 Removal
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
1.4.1 | Collectively support and coordinate annual cleanup events around land-based litter. | # cleanup events
# cleanup participants
# miles beaches cleaned
# pounds of trash removed
# pieces/items picked up

## Goal 1 Strategy 5
Goal 1: Understand, Prevent and Mitigate the Impacts of Single-Use Plastic and Other Water/ Land-based Consumer Debris
Strategy 1.5 Policy and Management
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
1.5.1 | Engage local, county, state, and/ or federal elected officials and policymakers to improve awareness of consumer debris policies and advocacy campaigns. | # resources developed/shared
# municipalities and policymakers engaged
1.5.2 | Inform, advocate and/or implement new local, municipal and state policies, management plans and/ or campaigns aimed at source reduction (e.g., balloons, single-use plastic and utensils, nip bottles), prevention and/or interception practices, informed by available marine debris collection data. (Crosscuts with 1.1.10) | # new policies implemented
# new management plans developed
# resources developed/shared
# new campaigns undertaken
1.5.3 | Develop a listserv for organizations that are interested in legislative opportunities that could benefit from additional information on consumer debris. | # listservs developed & maintained

## Goal 2 Strategy 1
Goal 2: Understand, Prevent and Mitigate the Impacts of Abandoned and Lost Fishing/ Aquaculture Gear
Strategy 2.1 Prevention, Education and Outreach
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
2.1.1 | Inventory existing best management practices to prevent or reduce abandoned and lost fishing/aquaculture gear and consider modifications for Long Island Sound with fishing and aquaculture industries, such as including biodegradable release requirements to lessen the impact of lost pots. | # Best Management Practices suitable for LIS
# Modifications undertaken
2.1.2 | Identify and share methods to properly dispose of end-of-life fishing/aquaculture gear. | # Methods/Best Management Practices shared
2.1.3 | Develop a campaign to identify and engage new partners in abandoned and lost fishing/aquaculture gear prevention programs. | # campaigns developed and implemented
2.1.4 | Engage with fishing and aquaculture businesses across the Sound to better understand debris issues, storm preparedness and information gaps. | # fishing and aquaculture businesses engaged
2.1.5 | Share gear innovation funding opportunities broadly with relevant stakeholders (e.g., recreational and commercial fishing and aquaculture industries, academic and non-profit researchers and any interested party). | # funding opportunities shared as available
2.1.6 | Share the advancement of gear innovations broadly with relevant stakeholders (e.g., recreational and commercial fishing and aquaculture industries and any interested party). | # successful gear innovations shared
# unsuccessful gear innovations shared
# innovations adopted
2.1.7 | Integrate marine debris issues into recreational fisheries action plans. | # recreational fisheries action plans incorporating marine debris issues
2.1.8 | Promote/share outreach products at targeted events (boat shows, trade shows, fishing expos, fishing shops) to engage the public, commercial and recreational fishing and boating communities in abandoned and lost fishing gear prevention. | # outreach events where outreach products promoted and shared
2.1.9 | Support translation of outreach products, signage and/or digital campaigns to non-English languages identified by the community. | # outreach products translated
2.1.10 | Create a one-pager for the recreational boating/diving community regarding the presence of gear in Long Island Sound and how to safely avoid it. | # one-pagers developed
# distributed
2.1.11 | Create and maintain an online data portal containing information on available research regarding derelict fishing gear to be updated annually. | # databases created and updated annually

## Goal 2 Strategy 2
Goal 2: Understand, Prevent and Mitigate the Impacts of Abandoned and Lost Fishing/ Aquaculture Gear
Strategy 2.2 Research Assessment, Wildlife Impacts and Monitoring
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
2.2.1 | Compile a report to document local knowledge regarding ghost fishing and species impacted by lost and abandoned fishing/ aquaculture gear. | # reports compiled and updated
2.2.2 | Engage with stranding networks, wildlife rehabilitation centers and the public to better understand and collect marine debris interaction data available for analysis. | # stranding networks and wildlife rehab centers contacted
# wildlife entanglements reported by networks and centers
# public/community science engagements on wildlife strandings
# wildlife entanglements reported through public/community science efforts
Summary of available data from relevant organizations/public reviewed and shared
2.2.3 | Engage with coastal land managers/refuges, community science programs to monitor and document the extent/types of abandoned gear on public/managed lands and cleanup costs. | # coastal land managers/refuges engaged
# community science programs engaged
Extent and types of abandoned gear on public/managed lands
Average cost per cleanup

## Goal 2 Strategy 3
Goal 2: Understand, Prevent and Mitigate the Impacts of Abandoned and Lost Fishing/ Aquaculture Gear
Strategy 2.3 Proper Disposal and Infrastructure
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
2.3.1 | Research successful abandoned and lost fishing/aquaculture gear prevention, recycling and disposal programs and evaluate for adaptation in Long Island Sound. | # suitable programs adopted for LIS
2.3.2 | With proper state permissions, coordinate directed fishing/ aquaculture gear disposal events in Long Island Sound communities. | # state/local authorities engaged
# partners engaged
# disposal events facilitated
# pounds of gear collected
# traps collected
# pounds recycled or disposed of sustainably
# traps recycled or disposed of sustainably
2.3.3 | Coordinate with state and local authorities, metal recyclers, waste-to-energy companies and haulers to host annual collection events to return or dispose of end-of-life fishing / aquaculture gear. | # state/local authorities engaged
# partners engaged
# collection events hosted
# pounds of gear collected
# traps collected
# pounds recycled or disposed of sustainably
# traps recycled or disposed of sustainably
2.3.4 | Modify existing or develop new outreach products on proper disposal and recycling of monofilament lines and share with fishers, boaters and the public. | # outreach products shared
2.3.5 | Support the installation, maintenance and proper use of monofilament disposal receptacles at priority locations in parks, fishing piers and marinas, including signage in English and non-English languages. | # new monofilament disposal receptacles installed
# new installation locations
Locations of new installations
2.3.6 | Inventory existing monofilament bins and bin-monitoring partners and update regularly. | # inventories and maps completed and updated annually
2.3.7 | Seek/share grant opportunities to support the prevention of abandoned and lost fishing/ aquaculture gear and its removal annually. | # funding opportunities shared as available
2.3.8 | Coordinate a protocol in which partners can share ideas for grant applications and ask for collaborators, help with matching funds, recommendation letters or other relevant resources. | Platform identified, shared and used by partners
2.3.9 | Inventory and map abandoned and derelict vessels in Long Island Sound. | # inventories and maps completed and updated annually
2.3.10 | Expand fiberglass/vessel recycling in Connecticut and New York. | # fiberglass recycling locations
# new recycling programs initiated
2.3.11 | Acquire and distribute reusable trash bags for commercial and charter fishing vessels. | # reusable trash bags distributed

## Goal 2 Strategy 4
Goal 2: Understand, Prevent and Mitigate the Impacts of Abandoned and Lost Fishing/ Aquaculture Gear
Strategy 2.4 Removal
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
2.4.1 | Maintain or acquire the necessary permits to remove abandoned and lost fishing gear. | # state permits maintained and utilized
2.4.2 | Coordinate and support removal of ALDFG (active dragging) regions working alongside commercial fishing and aquaculture industries with one data repository. | # pounds gear collected
# traps collected
# traps recycled
# pounds recovered gear recycled or sustainably disposed of
# industry partners involved
# species captured
# individuals captured
2.4.3 | Establish partnerships to remove and recycle traps and return usable, identifiable gear to its owners. | # new partnerships established
# traps returned to owners
2.4.4 | Investigate available technologies for detecting gear accumulations | Inventory of detection technologies completed
# new detection technologies used
2.4.5 | Establish protocols for access to equipment, haulers, storage sites, disposal/recycling sites for the removal of large quantities of fishing gear, docks and derelict vessels. | # protocols established and shared
2.4.6 | Identify and disseminate the processes involved and organizations and agencies responsible for removing abandoned and derelict vessels in Long Island Sound | Report of processes compiled
# derelict/abandoned vessels removed

## Goal 2 Strategy 5
Goal 2: Understand, Prevent and Mitigate the Impacts of Abandoned and Lost Fishing/ Aquaculture Gear
Strategy 2.5 Policy and Management
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
2.5.1 | Synthesize and convey results of lost and abandoned commercial/ aquaculture gear recovery programs to state fisheries and aquaculture managers to highlight the role of commercial and recreational fishing (lobster, rod-and-reel, blue crab) and aquaculture in generating and retrieving derelict gear. | # fisheries managers/industry members contacted
# reports submitted on type, quantity and location of gear recovered

## Goal 3 Strategy 1
Goal 3: Understand, Prevent and Mitigate the Impacts of Microplastics and Microfibers
Strategy 3.1 Prevention, Education and Outreach
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
3.1.1 | Create, maintain and share digital tools for sharing information and data products on microplastics and microfibers | # portals / digital tools created/maintained
# portal / digital tools shared
3.1.2 | Adapt existing/create new outreach products containing relevant microplastics and microfiber information, data, research, best practices, literature and/or funding resources and disseminate to the Long Island Sound marine debris community. | # outreach products and materials created
# outreach products and materials shared
3.1.3 | Create, adapt, use and/or share existing or new microplastics and microfibers lesson plans that align with Next Generation Science Standards where applicable, and/or Long Island Sound materials that have been successfully demonstrated to raise awareness of relevant microplastic and microfiber issues among P-12 students and P-12 grade educators through: ● online platforms ● in-person events ● educator workshops ● after-school programs and visits ● summer camps ● campaigns ● field trips (Crosscuts with 1.1.9) | # new lesson plans and educational materials created
# lesson plans and educational materials shared
# P-12 students engaged
# P-12 educators engaged

## Goal 3 Strategy 2
Goal 3: Understand, Prevent and Mitigate the Impacts of Microplastics and Microfibers
Strategy 3.2 Research Assessment, Wildlife Impacts & Monitoring
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
3.2.1 | Conduct and compile reviews of scientifically sound, peer-reviewed research literature on microplastic and microfiber research relevant to Long Island Sound. | # new literature reviews completed
# new papers published
3.2.2 | Seek/share grant opportunities to address Action Plan research priorities, including research, to study microplastics and microfibers in Long Island Sound. | # new funding opportunities shared
# new grants received
3.2.3 | Promote opportunities and engage with interested organizations to develop microplastics and microfiber monitoring programs in Long Island Sound and make the resulting information available to the public. | # M&M monitoring programs developed for LIS
# M&M monitoring programs implemented for LIS
3.2.4 | Conduct microplastic and/or microfiber focused webinar(s) or workshop(s) to share the latest research findings relevant to Long Island Sound and make them available to the public. | # new webinars/workshops
# presentation attendees

## Goal 3 Strategy 3
Goal 3: Understand, Prevent and Mitigate the Impacts of Microplastics and Microfibers
Strategy 3.3 Source Reduction
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
3.3.1 | Develop research initiatives focused on microplastic and microfiber intercept technologies with relevance to Long Island Sound; specific actions include: data gaps, data collection, develop industry partnerships, dissemination of results, etc. | # grants awarded for interception technologies for LIS
# new publications on intercept technologies
# outreach products/presentations on intercept technologies

## Goal 3 Strategy 4
Goal 3: Understand, Prevent and Mitigate the Impacts of Microplastics and Microfibers
Strategy 3.4 Policy and Management
Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
3.4.1 | Engage with local and state decisionmakers regarding microplastics and microfibers in Long Island Sound waterways, to: disseminate, create and advocate for new policies and regulations. | # local and state decision-makers engaged
# new policies or regulations related to M&M
3.4.2 | Support Extended Producer Responsibility legislation to hold manufacturers responsible for recovery of plastic waste | # local and state decision-makers engaged
# presentations delivered
# community members engaged

## Good Ideas but no Partners
Former Action # | Action | Metric | 2025-26 | Contributor/Comments | Links | 2026-27 | Contributor/Comments | Links
1.1.14 | Engage with restaurants and food service industries to educate about certification programs and highlight those that participate. | # restaurants & food service industries engaged in learning about programs
# restaurants & food service industries participating in programs
1.1.18 | Create a guide of actions, including associated cost/benefit analyses, for organizations within the Long Island Sound watershed related to the reduction of consumer debris. | # businesses engaged
# case studies/best practices shared
1.1.21 | Partner with wholesalers to offer restaurants, hotels, shops, tourist attractions, schools, colleges, houses of worship and nature centers cost-effective rates for bulk reusable, recyclable, or compostable items. | # wholesalers engaged
1.1.23 | Conduct gap analysis of marine debris tracking data using state reports from International Coastal Cleanup database and other sources to document trends in marine debris collected throughout the Long Island Sound watershed. Identify at-risk areas most affected by marine debris and pollution, develop new partnerships and provide tools and resources to support and increase the number of clean ups held annually. | # gap analyses conducted
# new partners engaged
# at-risk areas identified
# tools & resources distributed in support of additional cleanups
1.2.4 | Promote support for surveys using standard metrics to identify sources and types of consumer debris collected in water. | # standardized metrics for surveys developed and implemented
2.1.5 | Assist fishing and aquaculture businesses in finding cost-effective alternatives for plastic or disposable materials. | # fishing & aquaculture businesses engaged
# cost-effective alternatives identified and shared
3.1.7 | Engage with stakeholders such as construction and building companies, artificial turf, and tire manufacturers to share information regarding microplastic and microfibers. | # stakeholders engaged